## Defect Tracker
Defect ID | Sprint | Description | Severity | Reported By | Date Raised | Status | Date Closed | Resolution / Comments
DEF-01 | 2 | NameError: name 'model' is not defined when running M2 evaluation block independently. | High | Developer | 2025-12-18 | Closed | 2025-12-18 | Fixed: Consolidated M1 and M2 code into a single script execution flow.
DEF-02 | 2 | TypeError in TrainingArguments. evaluation_strategy keyword causes crash in newer Transformers version. | Medium | Developer | 2025-12-20 | Closed | 2025-12-20 | Fixed: Updated parameter to eval_strategy="epoch".
DEF-03 | 2 | ImportError: Accelerate library version mismatch or missing. | Critical | Developer | 2025-12-20 | Closed | 2025-12-21 | Fixed: Installed accelerate>=0.26.0 and restarted runtime.
DEF-04 | 2 | UndefinedMetricWarning: Precision is 0.0 for some labels in Baseline models. | Low | Developer | 2025-12-21 | Closed | 2025-12-22 | Accepted: Warning is expected for baseline models on imbalanced data; ignored as per project scope.
DEF-05 | 3 | False Positive Urgency: The word "know" triggers the "now" keyword rule, marking non-urgent emails as High. | High | Developer | 2026-01-04 | Closed | 2026-01-05 | Fixed: Updated keyword matching logic to use Regex \b (word boundaries) to match only whole words.
DEF-06 | 3 | Mismatch in Urgency Predictions: ML model over-predicts 'High' for medium priority tickets. | Medium | Developer | 2026-01-05 | Open | - | Mitigated: Hybrid system prioritizes recall (safety) over precision. Accepted as "Safety First" feature.